## Learning SIMPLIS (Engr) Process
Learning SIMPLIS Process
for New SIMPLIS Users
Objective:
Provide a process by which a capable and willing engineer can come up to speed with SIMPLIS in four (full time) weeks
At the conclusion of this experience, engineer will be confident that they will be able to competently apply SIMPLIS to appropriate switching power supply modeling objectives.
They won't know everything, but they will be confident that they know how to find out what they need to in order to do a competent job.
|  | Morning |  | Afternoon
Week 1:
Day 1:
|  | Begin SIMPLIS Tutorial |  | Complete SIMPLIS Tutorial
Study: What is SIMPLIS?
Research: What example SIMPLIS circuits are relevant to work user plans to do with SIMPLIS.
Day 2:
|  | Advanced SIMPLIS Training: |  | Outline SIMPLIS Simulation Project Objectives
|  | Module 1 - Overview of the SIMPLIS Environment |  | Identify meaningful project milestones with the goal of achieving as much value as early in the project as possible. In particular, idendify a valuable milestone to be met by mid afternoon on Day 5 to be presented to your manager.
| Day 3: | Advanced SIMPLIS Training:
|  | Module 2 - Advanced SIMPLIS |  | Begin SIMPLIS Simulation Project
( Complete all sections except 2.4. In section 2.4, make sure to at least scan the material so you can get an idea what is in there. )
| Day 4: | Advanced SIMPLIS Training:
|  | Module 3 - Getting Ready to Model |  | SIMPLIS Simulation Project - focus on your Day 5 milestone
| Day 5: | Advanced SIMPLIS Training:
|  | Module 4 - Introduction to Modeling |  | Complete Day 5 milestone & present to your manager
Week 2:
| Day 6: | Advanced SIMPLIS Training:
|  | Module 5 - Parameterization |  | Identify at least two IP Blocks that you can create as part of your project where you can employ the parameterization concepts that you have learned in the morning session.
| Day 7: | Complete the parameterization of at least one IP Block in your project. Choose the simplest block initially. |  | Continue work on your project with a focus on your Day 8 milestone. Refine Project Objectives and Requirements. Develop 4 to 5 additional milestones for the final 2.5 weeks of this project. Go over milestones with your manager.
| Day 8: | Advanced SIMPLIS Training:
|  | Application B - Switching Losses and Measuring Efficiency |  | Complete your Day 8 mileston & present to your manager
| Day 9: | Read documentation on:
- How to organize directories and SIMPLIS files
* for development
* for model distribution
- Use Copy Hierarchy for version control
| Day 10: |  |  | Complete Week 2 milestones
Week 3: |  | Address Week 3 milestones |  | Complete Week 3 milestones and present to manager
Week 4: |  | Complete Week 4 milestones and final project and present to manager